## Instructions
Instructions:
1 | Safe start up check list "SAFE start protocol" tab to be completed at least 7 days prior to resuming production
2 | Plant Manager to ensure all criteria are fully in place before prodution restart
3 | Regional Operations leader approval required before restart (per item 1.4 in checklist)
4 | If any criteria requires clarification you can reach out to regional operations leader or the Corporate element owner defined
5 | Improvements to existing check list can be communicated to either the Corporate Element owner or |  | simon.c.wright@aptiv.com
6 | All sites are rquired to follow this checklist per Policy letter issued in EOS | HOGL_5-3_MG_01_EN
7 | Criteria not complete can be seen in summary tab "Actions to be closed"
8 | Scoring / Completeness summary is available in tab "Charts"
Note: An online version of the protocol will be available in I-nexus in the coming few days and all sites will be instructed to use that version to update progress

## SAFE start protocol
Plant SAFE Start Protocol
Site Name: |  |  |  | Objective: |  |  |  | Responsible Owners
Date: |  |  |  | 1. Ability to secure a healthy workforce
Completed By: |  |  |  | 2. Ability to restart operations
3. Ability to restart supply chain
# | Major Elements | Scope |  | Key Criteria to check | In Place | Score |  | Corporate Lead | Site Element Owner | Plant | Regional | Global
[13 empty] | Target | Actual
1 | New Legal Requirements/ Stakeholder Mgt | Do we understand any new legal requirements or the minimum Aptiv standards in relation to COVID19? | 1.1 | Determine new legal requirements impacting, assess consequences and escalate any risk to re-start |  | 0 | FALSE | Tim Seitz | Plant Manager | X |  |  | 1 | 0
|  |  | 1.2 | Aptiv internal preparedness level 3 is defined and is confirmed to be in place per (HOGP_5-3_SE_37-A01_EN) |  | 0 | FALSE |  | Plant Manager | X | X | X | 1 | 0
|  |  | 1.3 | Obtain local/national authorizations to restart where required |  | 0 | FALSE |  | Plant Manager | X |  |  | 1 | 0
| HOGP_5-3_SE_37-A01_EN |  | 1.4 | Obtain internal approvals from regional operations leader to commence restart |  | 0 | FALSE |  | Plant Manager | X | X |  | 1 | 0
|  |  | 1.5 | Is support available from government to help protect employees and are we utilizing that support |  | 0 | FALSE |  | Plant Manager | X |  |  | 1 | 0
2 | Secure Health of Employees | Pre-return to work and site entry health controls are in place to minimize the risk to our employees and ability to run our operations | 2.1 | Health declaration forms provided to all employees, checked before entry to site (HOGP_5-3_SE_37-F01_EN) |  | 0 | FALSE | Aldo Gomez | EHS Manager | X |  |  | 1 | 0
|  |  | 2.2 | Country Level PPE availability is confirmed |  | 0 | FALSE |  | Regional Ops |  | X |  | 1 | 0
|  |  | 2.3 | Site has access to target of 25 days coverage of specified masks per preparedness Level 3 |  | 0 | FALSE |  | EHS Manager | X |  |  | 1 | 0
|  |  | 2.4 | Return to work controls defined for all employees and any high risk categories (HOGP_5-3_SE_37-A01_EN) |  | 0 | FALSE |  | EHS Manager | X |  |  | 1 | 0
|  |  | 2.5 | Sufficient temperature check equipment is available & protocol in place to safely measure on entry |  | 0 | FALSE |  | EHS Manager | X |  |  | 1 | 0
| HOGP_5-3_SE_38-F01_EN |  | 2.6 | Suspected employees should be tested immediately |  | 0 | FALSE |  | EHS Manager | X |  |  | 1 | 0
|  |  | 2.7 | Quarantine protocol defined if suspected infected employee identified at work (HOGP_5-3_SE_37-A01_EN) |  | 0 | FALSE |  | EHS Manager | X |  |  | 1 | 0
| HOGP_5-3_SE_37-A01_EN |  | 2.8 | Check site has identified and is in compliance with local/country legal requirements |  | 0 | FALSE |  | EHS Manager | X |  |  | 1 | 0
|  |  | 2.9 | Personal hygiene protocols are in place and monitored for effectiveness per (HOGP_5-3_SE_37-A01_EN) |  | 0 | FALSE |  | EHS Manager | X |  |  | 1 | 0
3 | Facility Readiness | The physical workplace is safe and clean to operate in, with clear guidelines on sanitation, segregation and emergency response plans and services | 3.1 | Full site disinfection executed prior to employees returning to work per HOGP_5-3_SE_38-F01_EN |  | 0 | FALSE | Tom Dempsey | EHS Manager | X |  |  | 1 | 0
|  |  | 3.2 | Cleaning routines established, executed and checked at specific frequency per Level 3 (HOGP_5-3_SE_37-A01_EN) |  | 0 | FALSE |  | EHS Manager | X |  |  | 1 | 0
|  |  | 3.3 | Canteen protocol established, executed and checked at specific frequency per Level 3 (HOGP_5-3_SE_37-A01_EN) |  | 0 | FALSE |  | EHS Manager | X |  |  | 1 | 0
|  |  | 3.4 | Break rules established, executed and checked at specific frequency per Level 3 (HOGP_5-3_SE_37-A01_EN) |  | 0 | FALSE |  | EHS Manager | X |  |  | 1 | 0
|  |  | 3.5 | Social distancing, segregation, gatherings rules communicated & enforced per Level 3 (HOGP_5-3_SE_37-A01_EN) |  | 0 | FALSE |  | EHS Manager | X |  |  | 1 | 0
|  |  | 3.6 | Water supply and food (vending) start up checks completed |  | 0 | FALSE |  | Facility Manager | X |  |  | 1 | 0
| HOGP_5-3_SE_38-F01_EN |  | 3.7 | Emergency response team is complete and contact information up-to-date |  | 0 | FALSE |  | EHS Manager | X |  |  | 1 | 0
|  |  | 3.8 | Waste water treatment system checks are complete |  | 0 | FALSE |  | Facility Manager | X |  |  | 1 | 0
| HOGP_5-3_SE_37-A01_EN |  | 3.9 | Check fire alarm and safety systems are meeting statutory requirements |  | 0 | FALSE |  | EHS Manager | X |  |  | 1 | 0
|  |  | 3.10 | Local emergency services confirmed available to support site start up (fire, police, medical) |  | 0 | FALSE |  | EHS Manager | X |  |  | 1 | 0
4 | Customer Ramp Up Planning | We understand our customers start up plan and requirements, and have a clear demand outlook to plan against | 4.1 | PC&L person identified to monitor & communicate EDI during closure and ramp up period |  | 0 | FALSE | Eric Lindstrom | PC&L Manager | X |  |  | 1 | 0
|  |  | 4.2 | Establish Finished Goods plan during ramp up plan to secure customer supply |  | 0 | FALSE |  | PC&L Manager | X |  |  | 1 | 0
|  |  | 4.3 | Customer ship to locations shutdown plan documented & maintained |  | 0 | FALSE |  | PC&L Manager | X |  |  | 1 | 0
|  |  | 4.4 | Single point of contact is established with key customers obtain real time customer start up info |  | 0 | FALSE |  | PC&L Manager | X | X |  | 1 | 0
|  |  | 4.5 | Process established to check normal payments terms are applied to shipments before release |  | 0 | FALSE |  | PC&L Manager | X |  |  | 1 | 0
5 | Manufacturing Readiness | Our equipment, processes & support services have been checked for readiness to restart with first time right quality | 5.1 | Specific people have been defined and are available to complete pre-start up activities and checks |  | 0 | FALSE | Simon Wright | Plant Manager | X |  |  | 1 | 0
|  |  | 5.2 | Equipment deep cleaning activities are complete (in particular with user interface) |  | 0 | FALSE |  | Facility Manager | X |  |  | 1 | 0
|  |  | 5.3 | Equipment readiness activities/checks are completed |  | 0 | FALSE |  | Plant Manager | X |  |  | 1 | 0
|  |  | 5.4 | Any specific quality safe launch plan activities in addition to standard are defined and implemented |  | 0 | FALSE |  | Quality Manager | X |  |  | 1 | 0
|  |  | 5.5 | Frequency of in process quality checks and layered audits is increased appropriately during start up period |  | 0 | FALSE |  | Quality Manager | X |  |  | 1 | 0
|  |  | 5.6 | Lab equipment is stored safely during shutdown, sanitization and re-calibration plans are in place |  | 0 | FALSE |  | Quality Manager | X |  |  | 1 | 0
|  |  | 5.7 | Confirm facilities (mechanical, electrical) start up checks are complete |  | 0 | FALSE |  | Facility Manager | X |  |  | 1 | 0
|  |  | 5.8 | Service providers have confirmed ability to support required activities |  | 0 | FALSE |  | Plant Manager | X |  |  | 1 | 0
|  |  | 5.9 | Utility & Waste disposal services are available as normal with no constraints |  | 0 | FALSE |  | Facility Manager | X |  |  | 1 | 0
|  |  | 5.10 | Standard site shutdown/restart checklist is in place and followed in addition to new requirements |  | 0 | FALSE |  | Plant Manager | X |  |  | 1 | 0
6 | People Availability | Our employees have real time information on start-up plans and we have the right skills required at the right time to support our customers | 6.1 | Establish daily remote comms channel to all employees (comms update & restart information eg. Whatsapp) |  | 0 | FALSE | Mark Paulek | HR Manager | X | X |  | 1 | 0
|  |  | 6.2 | Plan defined on how to prioritize who to bring back first (salaried, hourly) |  | 0 | FALSE |  | HR Manager | X |  |  | 1 | 0
|  |  | 6.3 | Staffing plan during shutdown period defined to maintain and prepare start up |  | 0 | FALSE |  | HR Manager | X |  |  | 1 | 0
|  |  | 6.4 | Temp/Contingent workforce re-hiring & training plan in place to support planned volumes |  | 0 | FALSE |  | HR Manager | X |  |  | 1 | 0
|  |  | 6.5 | Transportation services provided for employees have defined health controls in place & checked |  | 0 | FALSE |  | HR Manager | X | X |  | 1 | 0
|  |  | 6.6 | Critical skills (specific roles) availability define and plan in place to support ramp up |  | 0 | FALSE |  | HR Manager | X |  |  | 1 | 0
|  |  | 6.7 | Pre-return to work health checks requirements are clearly defined and communicated (declaration of exposure) |  | 0 | FALSE |  | HR Manager | X | X |  | 1 | 0
7 | Supplier Readiness | We understand our suppliers readiness & risks along with any capacity gaps based on supplier lead times & our inventory positon | 7.1 | Supplier facility & workforce planning assessment complete per Aptiv guidance - site to check with SCM support |  | 0 | FALSE | Eric Lindstrom | Commodity Mgt |  | X | X | 1 | 0
|  |  | 7.2 | Supplier restart plans have been verified to support our start up plans - site to check with SCM support |  | 0 | FALSE |  | Commodity Mgt |  | X | X | 1 | 0
|  |  | 7.3 | Supplier capacity check is complete against next 3-6 months current demand - site to check with SCM support |  | 0 | FALSE |  | Commodity Mgt |  | X | X | 1 | 0
|  |  | 7.4 | Constrain supply list by component is available and actioned by SCM at appropriate frequency |  | 0 | FALSE |  | PC&L Manager | X | X | X | 1 | 0
|  |  | 7.5 | On hand/current coverage of components - clear to build available to support first full week of production |  | 0 | FALSE |  | PC&L Manager | X |  |  | 1 | 0
|  |  | 7.6 | In transit material status is understood |  | 0 | FALSE |  | PC&L Manager | X |  |  | 1 | 0
|  |  | 7.7 | Lead time and ramp up plan with long lead suppliers is reflected in current EDI signals |  | 0 | FALSE |  | PC&L Manager | X |  |  | 1 | 0
|  |  | 7.8 | Financial consideration around payment terms checked (any differences to standard terms) - site to check with SCM |  | 0 | FALSE |  | Commodity Mgt |  | X | X | 1 | 0
8 | Logistics planning (Warehousing) | Potential logistics 7 warehousing constraints are identified with mitigation plans in place | 8.1 | Transport restrictions linked to in country or cross border goods movement are understood |  | 0 | FALSE | Eric Lindstrom | Global Logistics |  | X | X | 1 | 0
|  |  | 8.2 | Alternate providers / routes have been defined with support of corporate logistics teams |  | 0 | FALSE |  | Global Logistics |  | X | X | 1 | 0
|  |  | 8.3 | Truck driver physical controls in place and checked to manage segregation during drop off and pick up |  | 0 | FALSE |  | PC&L Manager | X |  |  | 1 | 0
|  |  | 8.4 | Required warehousing operations to support factory ramp up are in place (internal or 3PL) |  | 0 | FALSE |  | PC&L Manager | X |  |  | 1 | 0
9 | Inventory planning | Value chain Inventory positions are understand and material is only committed when needed by customer | 9.1 | Component inventory status/coverage is understood and targets defined |  | 0 | FALSE | Eric Lindstrom | PC&L Manager | X |  |  | 1 | 0
|  |  | 9.2 | Projection on Finished goods in place assuming aligned demand view with PC&L and Sales |  | 0 | FALSE |  | PC&L Manager | X |  |  | 1 | 0
|  |  | 9.3 | Inventory storage is secure during shutdown and material shelf life is actively managed and check pre-start up |  | 0 | FALSE |  | PC&L Manager | X |  |  | 1 | 0
|  |  | 9.4 | Spare parts inventory for key equipment is checked and confirmed pre-start up |  | 0 | FALSE |  | PC&L Manager | X |  |  | 1 | 0
10 | Management Planning Requirements | Management teams have routines in place to check progress, implement contingency plans and lessons learnt | 10.1 | Formal review mechanism is established for management team to assess pre-planning and readiness for start up |  | 0 | FALSE | Simon Wright | Plant Manager | X |  |  | 1 | 0
|  |  | 10.2 | High risk areas of concern identified with mitigation actions included in start up plan |  | 0 | FALSE |  | Plant Manager | X |  |  | 1 | 0
|  |  | 10.3 | Contingency plan established, reviewed and confirmed to be up to date |  | 0 | FALSE |  | Plant Manager | X |  |  | 1 | 0
|  |  | 10.4 | Duration required for execution of pre-start up activities in defined (in days) to ensure sufficient planning & comms |  | 0 | FALSE |  | Plant Manager |  |  |  | 1 | 0
|  |  | 10.5 | Significant changes to processes, equipment, tooling are validated and communicated (internal, customer) |  | 0 | FALSE |  | Plant Manager | X |  |  | 1 | 0
|  |  | 10.6 | Lessons learnt for future shutdown and restart activities identified, reviewed and incorporated into procedures |  | 0 | FALSE |  | Plant Manager | X | X | X | 1 | 0
[13 empty] | 68 | 0
Version 1.0

## Charts
100%
# | Major element | Tar | Act | % Tar | % Act
1 | New Legal Requirements / Stakeholder Mgt | 5 | 0 | 100% | 0%
2 | Secure Health of Employees | 9 | 0 | 100% | 0%
3 | Facility Readiness | 10 | 0 | 100% | 0%
4 | Customer Ramp Up Planning | 5 | 0 | 100% | 0%
5 | Manufacturing Readiness | 10 | 0 | 100% | 0%
6 | People Availability | 7 | 0 | 100% | 0%
7 | Supplier Readiness | 8 | 0 | 100% | 0%
8 | Logistics Planning (Warehousing) | 4 | 0 | 100% | 0%
9 | Inventory Planning | 4 | 0 | 100% | 0%
10 | Management Planning Requirements | 6 | 0 | 100% | 0%

## Actions to be closed
Major element | Open items | Owner | Date expected to close | #
New Legal Requirements/ Stakeholder Mgt | Is support available from government to help protect employees and are we utilizing that support | Plant Manager |  | 1
| Aptiv internal preparedness level 3 is defined for the site and is confirmed to be in place | Plant Manager |  | 4
| Obtain local/national authrorizations to restart where required | Plant Manager |  | 3
0
0
Major element | Open items | Owner | Date expected to close
Secure Health of Employees | Return to work controls defined for all employees and any high risk categories (per preparedness plan docs) | EHS Manager |  | 6
| Personal hygiene protocols are in place and monitored for effectiveness (hand sanitation, masks) | EHS Manager |  | 1
| Health declaration forms provided in advance to all employees and check on return to work before entry | EHS Manager |  | 9
| Site has access to target of 25 days coverage of specified masks per preparedness Level 3 | EHS Manager |  | 7
| Quarantine protocol defined if suspected infected employee identified at work (per preparedness plan docs) | EHS Manager |  | 3
| Check site has identified and is in compliance with local/country legal requirements | EHS Manager |  | 2
0
0
0
Major element | Open items | Owner | Date expected to close | #
Facility Readiness | Rules around breaks established, executed and checked at specific frequency per Level 3 | EHS Manager |  | 7
| Emergency response team is complete and contact information up-to-date | EHS Manager |  | 4
| Full site disinfection executed prior to employees returning to work | EHS Manager |  | 10
| Cleaning routines (daily/shift) established, executed and checked at specific frequency per Level 3 | EHS Manager |  | 9
| Waste water treatment system checks are complete | Facility Manager |  | 3
0
0
0
0
0
Major element | Open items | Owner | Date expected to close | #
Customer Ramp Up Planning | PC&L person identified to monitor & communicate EDI during closure and ramp up period | PC&L Manager |  | 5
| Process established to check normal payments terms are applied to shipments before release | PC&L Manager |  | 1
0
0
0
Major element | Open items | Owner | Date expected to close | #
Manufacturing Readiness | Specific people have been defined to complete pre-start up activities and checks | Plant Manager |  | 10
| Equipment deep cleaning activities are complete (in particular with user interface) | Facility Manager |  | 9
| Standard quality safe launch plan is developed and implemented during startup | Quality Manager |  | 7
| Service providers have confirmed ability to support required activities | Plant Manager |  | 3
| Utility & Waste disposal services are available as normal with no constraints | Facility Manager |  | 2
| Standard site shutdown restart procedure is in place and followed in addition to new requirements | Plant Manager |  | 1
0
0
0
0
Major element | Open items | Owner | Date expected to close | #
People Availability | Establish daily remote comms channel to all employees (comms update & restart information er. Whatsapp) | HR Manager |  | 7
| Critical skills (specific roles) availability define and plan in place to support ramp up | HR Manager |  | 2
| Staffing plan during shutdown period defined to maintain and prepare start up | HR Manager |  | 5
| Temp/Contingent workforce re-hiring & training plan in place to support planned volumes | HR Manager |  | 4
0
0
0
Major element | Open items | Owner | Date expected to close | #
Supplier Readiness | Supplier facility & workforce planning assessment complete per Aptiv guidance | Commodity Mgt |  | 8
| Financial consideration around payment terms checked (any differences to standard terms) | Commodity Mgt |  | 1
| Supplier restart plans have been verifried to support our start up plans | Commodity Mgt |  | 7
| Constrain supply list by component is available and actioned by SCM at appropriate frequency | PC&L Manager |  | 5
| In transit material status is understood | PC&L Manager |  | 3
0
0
0
Major element | Open items | Owner | Date expected to close | #
Logistics planning (Warehousing) | Transport restrictions linked to in country or cross border goods movement are understood | Global Logistics |  | 4
| Required warehousing operations to support factory ramp up are in place (internal or 3PL) | PC&L Manager |  | 1
0
0
Major element | Open items | Owner | Date expected to close | #
Inventory planning | Spare parts inventory for key equipment is checked and confirmed pre-start up | PC&L Manager |  | 1
| Projection on Finished goods in place assuming aligned demand view with PC&L and Sales | PC&L Manager |  | 3
0
0
Major element | Open items | Owner | Date expected to close | #
Management Planning Requirements | Lessons learnt for future shutdown and restart activities identified, reviewed and incorporated into procedures | Plant Manager |  | 1
| Formal review mechanism is established for management team to assess pre-planning and readiness for start up | Plant Manager |  | 5
| High risk areas of concern identified with mitigation actions included in start up plan | Plant Manager |  | 4
| Significant changes to processes, equipment, tooling are validated and communicated (internal, customer) | Plant Manager |  | 2
0
Click here to
sort the data

## Revision history
Date | Revision details
2020-04-10 | HOGP_5-3_SE_38-F01_EN Disinfection checklist (Level 2, 3 & 4) added to Section 3 of Plant SAFE Start Protocol – Checklist